## Instructions
D2 Agent Assistant — Phase 1 (AI Onboarding Coach MVP) Test Plan
How to verify Phase 1 is complete. Run each case on the 'Test Cases' tab, record the result, then complete the 'Sign-off' tab.
Purpose
Phase 1 = the AI Onboarding Coach MVP (per the D2&Co proposal). Note: the proposal numbers phases from 0, so this maps to the internal roadmap 'Phase 2'. A pilot agent should get a useful, D2-specific, cited answer in their pocket at 11pm — plus onboarding tracking, stall nudges, escalation, and admin KB management.
Before you start — prerequisites
Environment | The app running at http://localhost:3000 (npm run dev) or the deployed URL.
Test accounts | A New Agent (e.g. agent@web.com); a Senior Coach (coach@web.com) with that agent in their downline; an Admin (admin@web.com). Password same as email.
Seed data | Knowledge Base documents with real D2 content (project briefs, sales SOPs, channel playbooks), published in English, Bahasa Malaysia AND 中文.
Devices | A phone or a mobile-sized browser window (the chat is mobile-first).
Background jobs | Stall/escalation jobs run 'on-visit' — sign in as an authorized user and load the app to trigger any due jobs (there is no overnight scheduler).
Languages | Test in English, Bahasa Malaysia, and 中文.
How to fill this in
1 | Work down the 'Test Cases' tab. For each row, follow 'Steps' and compare with 'Expected Result'.
2 | Set the 'Result' cell (yellow) using the dropdown: Pass / Fail / Blocked / Not Run. It starts as 'Not Run'.
3 | Put anything you observed (screens, error text, the actual behaviour) in 'Actual / Comments' (yellow).
4 | 'Known Status' flags cases that are expected to FAIL on the current build (features built but not yet wired live) — record the real result anyway.
5 | When done, open the 'Sign-off' tab: mark the 5 success criteria + pilot gate, and give an overall Go / No-Go.
Priority | P0 = must work for Phase 1 to ship · P1 = important · P2 = polish.
Only edit the yellow cells | Result and Actual / Comments on 'Test Cases'; and the yellow cells on 'Sign-off'.
Example (how a filled row looks — do not edit here)
ID | Test Case | Steps | Expected Result | Result | Actual / Comments
B9 | Upfront AI disclosure | Open the chat for the first time (clear the disclosure ack). | A blocking 'this uses AI' notice appears before chatting. | Pass | Modal showed on first load; AI badge stayed in the header after.

## Test Cases
ID | Area | Test Case | Priority | Preconditions | Steps | Expected Result | Result | Actual / Comments | Known Status
A · User interface & chat surface
A1 | UI / Theme | Brand theme applied | P1 | Any signed-in account | Load any page (chat, sign-in, an admin page). | Warm off-white background; lime-green primary buttons with dark text; text is easily readable; focus rings visible on inputs. | Not Run
A2 | UI / Nav | Chat top navigation | P1 | Signed in as an agent; desktop width | Open the chat page. | Top bar shows: D2 logo, 'D2 Agent Assistant', an 'AI' badge, a centered Auto/Coach/Finder/Reply control (Auto active), EN/BM/中文 toggles, and a 'Talk to my coach' button. | Not Run
A3 | UI / Hero | Personalized greeting | P1 | Signed-in agent with a display name; empty chat | Open a new/empty chat. | Hero reads 'Hi {first name}, ready to close your first deal?' in a serif font; greets by the agent's name (graceful fallback if no name). | Not Run
A4 | UI / Hero | Suggestion cards | P2 | Empty chat | Look at the empty state. | A 2×2 grid of suggestion cards (Finder, Coach, Reply, Coach) each with an example prompt. | Not Run
A5 | UI / Chat | Tapping a suggestion sends it | P1 | Empty chat | Tap the 'Walk me through my first Meta ad campaign' card. | Coach mode is selected and the prompt is sent; a reply streams in. | Not Run
A6 | UI / Chat | Reply card asks for a lead | P2 | Empty chat, no active lead | Tap the 'Draft: loan eligibility…' (Reply) card. | Reply mode is selected and a 'which lead?' selector opens BEFORE anything is sent. | Not Run
A7 | UI / Chat | Mode tabs switch pillar | P1 | In a chat | Click Coach, then Finder, then Reply. | The active pill moves; the next message is handled by the chosen mode. | Not Run
A8 | UI / Chat | Message input behaviour | P1 | In a chat | Type a message; press Enter; then try Shift+Enter. | Enter sends; Shift+Enter adds a new line; the lime send button is disabled while a reply is streaming. | Not Run
A9 | UI / Disclosure | Footer AI disclosure | P1 | In a chat | Look just under the input box. | Persistent text: 'You're chatting with AI. Escalate to your coach any time.' | Not Run
A10 | UI / Mobile | Mobile-first layout | P0 | Phone or narrow (<640px) viewport | Open the chat on a phone-sized screen. | Nav collapses cleanly; suggestion cards stack to one column; the surface is comfortably usable one-handed. | Not Run
A11 | UI / i18n | Trilingual chat UI | P1 | — | Open /ms/chat and /zh/chat. | Hero, subtitle, suggestion prompts and footer all appear in Bahasa Malaysia / 中文. | Not Run
A12 | UI / History | Separate chat sessions | P1 | Signed-in agent | Send a message; open history → 'New conversation'; send another message; open history again. | TWO separate conversations, each titled by its first message; messages are NOT merged into one thread. | Not Run
A13 | UI / History | History loading state | P2 | Agent with past conversations | Open the conversation-history drawer. | Skeleton placeholder rows appear while it loads (not a blank or stale list). | Not Run
B · Coach MVP scope (core Phase 1)
B1 | Coach / Chat | Persistent chat history | P0 | Signed-in agent | Send a message; refresh the page; reopen the conversation from history. | The reply streams token-by-token; the conversation persists across a refresh and across sessions. | Not Run
B2 | Coach / Grounding | D2-grounded, cited answers | P0 | KB seeded with D2 content | Ask a real D2 training/project question (e.g. 'pricing structure for Royal Suites'). | The answer is grounded in D2's KB and cites sources (e.g. [KB:…]); it is NOT generic real-estate advice. | Not Run
B3 | Coach / Help | Help question gives guidance, not an alert | P1 | Signed-in agent | Type 'what can you do' or 'hi'. | A short, friendly overview of Coach / Finder / Reply and how Auto + the mode tabs work — NOT the 'no article / coach notified' alert. | Not Run |  | Recently fixed — should PASS.
B4 | Coach / Escalation | KB miss escalates to the coach | P1 | KB seeded; a senior coach assigned | Ask a D2 question you know is NOT in the KB. | The agent sees a 'couldn't find an article — coach notified' message AND an escalation / knowledge-gap appears on the senior coach's dashboard. | Not Run |  | KNOWN GAP: the live route shows the toast but does not yet write the escalation/gap row. Expected to FAIL until wired.
B5 | Coach / Journey | Onboarding checkpoint awareness | P1 | Agent mid-onboarding | Ask the Coach 'where am I in my onboarding?' | The Coach is aware of the agent's stage/checkpoint and tailors its answer. | Not Run |  | KNOWN GAP: journey context not injected into the live Coach. Expected to FAIL until wired.
B6 | Coach / Journey | Checkpoint advancement | P1 | Agent at a checkpoint with a comprehension check | Complete the comprehension check (paraphrase the concept in your own words). | The checkpoint advances and the agent's profile updates. | Not Run |  | KNOWN GAP: advancement is not wired to any action. Expected to FAIL until wired.
B7 | Coach / Stall | Proactive stall nudge (2 days) | P1 | An agent idle 2+ days | Simulate 2+ days of no activity, then load the app as an authorized user (triggers on-visit jobs). | A proactive nudge fires and a stall alert appears on the senior-coach dashboard. | Not Run |  | KNOWN GAP: last-active time isn't updated on use, so stalls aren't activity-driven. Expected to FAIL until wired.
B8 | Coach / Stall | Auto-escalate after 48h | P1 | A fired nudge, unanswered 48h | Leave the nudge unanswered for 48h (within working hours). | The case auto-escalates and is visible to the senior coach. | Not Run |  | KNOWN GAP: depends on the same last-active time. Expected to FAIL until wired.
B9 | Coach / Disclosure | Upfront AI disclosure | P0 | First-ever visit (clear the disclosure ack) | Open the chat for the first time. | A blocking 'this uses AI' notice appears before chatting; afterwards a persistent AI badge + footer remain. | Not Run
B10 | Coach / Handoff | Human handoff with context | P1 | In a chat | Click 'Talk to my coach'. | The handoff fires; the senior coach is notified with a PII-free context bundle; a success toast shows. | Not Run
B11 | Admin / KB | Plain-language KB management | P0 | Admin account | As admin, create/edit/publish a KB document; then as an agent, ask the Coach about it. | The document is saved with NO engineer involved, and the Coach can retrieve/cite it. | Not Run
B12 | Admin / Logs | Conversation log viewer | P1 | Admin account | As admin, open a conversation from the conversation log. | The transcript is viewable read-only and the access is audited. | Not Run
B13 | Coach / Dashboard | Senior-coach downline visibility | P0 | Senior coach with a downline | As the coach, open the dashboard. | The coach sees ONLY their own downline: each agent's stage/checkpoint/days, plus a stall inbox. | Not Run
B14 | Coach / i18n | Multilingual answers (EN/BM/中文) | P0 | KB seeded in 3 languages | Ask questions in EN, BM and 中文; also try the reply-language toggle. | UI copy is localized; the reply comes back in the right language; per-message language is auto-detected. | Not Run
B15 | Router | Intent routing + manual override | P1 | — | In Auto, ask a Finder-style question; then pin a specific mode via the tab. | The router sends it to the right specialist; the mode tab forces the chosen pillar. | Not Run
B16 | Admin / Model | Model-agnostic provider | P1 | Admin account | In admin Model config, change the model for a pillar; send a message. | The new model is used; no model IDs are hard-coded (they resolve from config). | Not Run
B17 | PDPA | PII pseudonymization + audit | P0 | — | Send a message containing a phone number / IC / email. | The PII is tokenized before it reaches the model; an append-only audit row (hashes only) is written. | Not Run
C · Admin & management (supporting surfaces)
C1 | Nav | Sidebar active state | P2 | Admin account | Visit Home, then Dashboard, then Knowledge Base. | Only the CURRENT section is highlighted in the sidebar (Home is not always highlighted). | Not Run |  | Recently fixed — should PASS.
C2 | Users | Coach reassignment reflects on Users | P1 | Admin; an agent + a coach exist | Reassign the agent's coach on /coach-assignment, then open /users. | The 'Senior coach' column on /users shows the NEW coach. | Not Run |  | Recently fixed — should PASS.
C3 | Cohorts | Add / remove agents in a cohort | P1 | Admin; a cohort + some new-agents exist | On /cohorts open 'Manage agents' → add an agent (count +1) → remove an agent (count −1). | Membership updates live; the agent count reflects it; the change is audited. | Not Run |  | New feature — should PASS.
C4 | Agents | Agent profile readability | P2 | Admin/coach; an agent in a cohort | Open an agent's profile page. | The email is dark and readable; the cohort shows its NAME (not the raw id). | Not Run |  | Recently fixed — should PASS.

## Sign-off
Phase 1 — Definition of Done & Sign-off
Phase 1 is complete when all five success criteria pass and the pilot gate is met. Fill the yellow cells.
Result summary (auto — from the Test Cases tab)
Total test cases | 34
Passed | 0
Failed | 0
Blocked | 0
Not run | 34
Success criteria (all must be TRUE)
Criterion | Result | Notes
SC1 — A pilot agent gets D2-grounded, cited answers (never generic) on a mobile surface, in EN/BM/中文 with auto-detect. (see B1, B2, B14, A10) | Not Tested
SC2 — Upfront AI disclosure + 'talk to my coach' handoff with full context + a KB miss auto-escalates to the senior coach. (see B9, B10, B4) | Not Tested
SC3 — A 2-day proactive nudge fires; after 48h it auto-escalates; visible as a stall alert on the coach dashboard. (see B7, B8, B13) | Not Tested
SC4 — An admin can create/edit/version KB in plain language (no engineer) and the Coach can retrieve it. (see B11) | Not Tested
SC5 — A senior coach sees only their own downline's stage + questions and can correct the AI inline. (see B13) | Not Tested
Pilot gate (M-03) — 5–10 pilot agents onboarded; escalation flow rehearsed with seniors; admin trained on KB updates. | Not Tested
Overall verdict (GO / NO-GO)
Tester name
Role
Date
Summary / blockers